Project Plan

Document Number: [02]

Date: 2 September 2025

[OwlExchange – A Modular eCommerce Platform for Community Use]

[Devin Perry, Scott Nguyen, Bee Tillman, Dawson White, Evan Tucker]

[Assurant Global Technology]

Table of Contents

1.	Introduction	3

2.	Project Overview	3

2.1	Scope	3

2.1.1	Identification	3

2.1.2	System Overview	3

2.1.3	Document Overview	3

2.2	Current System or Situation	3

2.3	Background, Objectives, and Scope	3

2.4	Operational Policies and Constraints	3

2.5	Description of Current System or Situation	3

2.6	Users or Involved Personnel	4

3.	Development Background/Approach	4

3.1	High Level Estimates	4

3.2	Key Contacts and Stakeholders	4

4.	Features, Primary Deliverables, and External Commitments	4

4.1	Feature List	4

4.2	Customer Deliverables	4

5.	Project Schedule	4

5.1	Major Project Milestones	4

5.2	Project Status Tracking & Working Meeting Minutes	5

6.	Project Work and Product Estimates	5

6.1	Estimate Summary	5

7.	Project Resource Requirements	6

7.1	Staffing/ Skill Requirements	6

7.2	Plan to Fill Skill Gaps	6

8.	Dependencies and Constraints	6

8.1	Constraints	6

9.	Risk Management	6

9.1	Risk Management Strategy	6

9.2	Initial Risk List	6

10.	Project Configuration and Data Management	7

10.1	Configuration Management	7

11.	Project Process	7

11.1	Software Life Cycle Model	7

12.	Referenced Documents	7

13.	Glossary	7

14.	Change Record	7

# Introduction

The OwlExchange project is a community-focused modular eCommerce platform sponsored by Assurant Global Technology, with the guidance from our mentors Robert Fortunato and Norbert Monfort, designed as a multi-semester capstone initiative. OwlExchange aims to provide a centralized web application that allows college users to donate, exchange and resell household and personal items in a structured, user-friendly and efficient way. This project is being developed in phases, beginning with a Minimum Viable Product (MVP) this semester, which focuses on creating clean modular architecture to enable extensibility. The MVP will implement essential platform features such as account creation, item listing, keyword and category-based search, item detail views, and a basic workflow for expressing interest in exchanges or requests. We will provide technical documentation and developer resources for future teams, define a clear feature roadmap that extends additional semesters, and expose well-defined interfaces for integration of future modules.

# Project Overview

## Scope

### Identification

OwlExchange is a modular eCommerce web platform designed for community use, developed under the sponsorship of Assurant Global Technology. The project is officially titled OwlExchange, this document applies to the MVP release, identified as Version 1.0. OwlExchange MVP is implemented in React and JavaScript for the front-end interface, Node.js and Express.js on the back end, and Microsoft SQL server (MS SQL) as the database management system. Core functionalities include account creation, login/logout, item listing and search, item posting, item detail pages, a basic exchange/request workflow and an initial admin dashboard. This release establishes the baseline modular architecture, documentation, and scaffolding required for future multi-semester expansions and advanced features.

### System Overview

OwlExchange provides a modular eCommerce platform that supports donation, exchange and resale of household and personal items within college communities. The system, developed using React, JavaScript, Node.js, Express.js, and MS SQL, is designed as a scalable and extensible web application to support multi-semester enhancements. This project is sponsored by Assurant Global Technology, with the guidance from our mentors Robert Fortunato and Norbert Monfort guiding the student development team, who serve as the developers and maintainers. This project is a web-based application with supporting documents that include the system roadmap, developer guide, and technical document that defines the baseline architecture and future integration pathways.

### Document Overview

Security considerations include the implementation of a login and authentication system to protect user accounts. The system will use MS SQL to add extra protection and a place to store users' personal information. We will also strive to have secure access to item postings and exchanges.

## Current System or Situation

At the moment, there is no dedicated platform for students or community members to exchange, donate, or resell items in an organized way. People rely on social media groups, campus boards, or word of mouth, but these methods are unstructured and lack features like secure logins, item filtering, or admin oversight.

This semester, our team is building the Minimum Viable Product (MVP) for OwlExchange. The MVP will introduce the essential tools missing from the current situation: account creation, item posting, search by keyword or category, item detail pages, and a simple workflow to show interest in items. We are also including a basic admin dashboard so moderators can manage users and listings. By focusing on this MVP, we’re addressing the biggest gaps in the current system and laying the foundation for future features like messaging, recommendations, and analytics.

## Background, Objectives, and Scope

OwlExchange provides a modular eCommerce platform that supports donation, exchange and resale of household and personal items within college communities. Its mission is to deliver a secure, modular, and user-friendly system in the development of an MVP including account management, item posting, item search, and basic administrative controls, while establishing a foundation for future feature expansion.

## Operational Policies and Constraints

The operation of the Owl Exchange system follows standard policies for user authentication, item posting, and community moderation to ensure a safe and trustworthy environment. Access to the platform is restricted to users through a secure login system, while administration has additional privileges to monitor and manage user activity. Constraints of the current system include limited functionality to core MVP features, reliance on React, JavaScript and MS SQL technologies, and the absence of advanced features like item ratings and recommendations which are planned for future phases.

## Description of Current System or Situation

The current system operates in a regular-use state without distinct modes such as training, degraded, or emergency, and is designed for a stable web-based environment accessible through standard browsers. Its major components include a React/JavaScript front end that provides the login screen, login and logout functions, and user interface, a Node.js/Express.js back end responsible for authentication and workflow logic, and a Microsoft SQL Server database for secure storage and retrieval of user and item data. These components communicate through REST APIs, while external interactions are limited to administrative deployment and database management procedures. The system currently supports account login/logout, item posting and search, item detail display, and a basic exchange workflow, with inputs such as user credentials and item data producing outputs like authenticated sessions, listings, and transaction confirmations. Performance is optimized for moderate community use, providing responsive page loads and reliable query handling, while the modular design supports maintainability, scalability, and usability. Quality attributes include reliability through tested core functions, portability via browser-based access, and flexibility for future feature integration. Provisions for security, privacy, and continuity are implemented through password protection, controlled access, database backup/recovery procedures, and a secure firmware foundation that ensures operational stability.

## Users or Involved Personnel

The primary users of the OwlExchange system are college students and community members who wish to donate, exchange, or resell household and personal items. These users require a simple and reliable interface for creating accounts, listing items, searching by category or keyword, and expressing interest in exchanges. Their responsibilities primarily include maintaining accurate item listings, engaging respectfully with other users, and following community guidelines.

Administrative users, such as system moderators, have elevated privileges within the platform. They are responsible for monitoring activity, managing inappropriate or duplicate listings, and ensuring that the community remains safe and trustworthy. Administrators also support the onboarding of future development teams by maintaining documentation and providing oversight of the evolving system.

Project sponsors and mentors from Assurant Global Technology serve as stakeholders and advisors. Their role includes providing feedback on feature development, ensuring alignment with industry practices, and guiding the student team in producing clean, modular, and maintainable code. Together, these groups form the foundation of the OwlExchange project’s community and support structure.

## Standards to follow

Covers the full development life cycle – IEEE 12207 defines processes for planning, developing, operating, maintaining, and retiring software systems, Since OwlExchange is meant to be scalable, extensible, and developed across multiple semesters, this standard ensures consistency and continuity for future student developers.

# Development Background/Approach

The OwlExchange system is being developed as a web-based application targeting desktop and mobile browsers, with the goal of providing a scalable and modular eCommerce platform for donation, exchange, and resale of household and personal items within the college communities. The front-end is built using React and JavaScript, while the backend leverages Microsoft SQL Server for data management and integration. Development takes place in a collaborative environment using modern version control and project management tools to ensure maintainability and multi-semester continuity.

The development team is composed of student developers who are responsible for implementation, testing, and documentation, supported by industry mentors from Assurant Global Technology who provide guidance on best practices and architectural direction. This structure simulates a professional development environment while fostering learning and knowledge transfer between academic and technical documentation, ensure that the platform can be extended, maintained, and integrated with future enchantments over multiple semesters.

## High Level Estimates

Total Effort: 250-300 hours

Lines of code: ~4000

Duration: ~16 weeks

## Key Contacts and Stakeholders

Sponsored by Assurant Global Technology: Provided the requirements for the project

Mentors Robert Fortunato and Norbert Monfort: Provides guidance on best practices and architectural direction. This structure simulates a professional development environment while fostering learning and knowledge transfer between academic and technical documentation, ensure that the platform can be extended, maintained, and integrated with future enchantments over multiple semesters.

# Features, Primary Deliverables, and External Commitments

## Feature List

User accounts- creation, login, logout

Search- keyword and categories

Dashboard- moderation tools

Item view- full item description and info

## Customer Deliverables

The deliverables for OwlExchange are planned to be presented to the sponsor on various dates throughout the second half of 2025. The first one is slated for September 22nd, and this is simply an official presentation of the project plan template detailing what is to be expected and how it will be completed. The next delivery on October 6th is the design document or SDS. The SDS will outline the specific planned architecture of the software along with the rationale behind all the decisions. October 27th is the first big milestone which will include all previous planning documents in addition to roadmap definition and all wireframes created thus far. Core and current MVP development as well as the modular scaffolding or placeholder for future features that will be handled by the next round of developers on OwlExchange will be delivered as part of milestone 2 on November 3rd. A test document detailing how the features will be tested against agreed upon metrics will be presented on December 1st. December 12th will see the delivery of milestone 3 which is comprised of all testing, documentation, roadmap finalization, and a sponsor walkthrough. Finally, on December 16th, a user manual and final version of all deliverables will be submitted.

# Project Schedule

## Major Project Milestones

| Date (YYYY-MM-DD) | Milestone/ task | Deliverable | Remarks |
| --- | --- | --- | --- |
| 9/16/ 2025 | Created the login screen | Login screen working | Was able to connect the regular user and Administrator dashboards to the login screen |
| 9/17/2025 | Finished Wireframe | Wireframes | Finished the base of what we wanted our wireframe to look like with AI. |
| 9/18/2025 | Planning MVP with MoSCOW Model | Completed part of MVP panning | We discussed and filled out the MoSCOW model to plan out the MVP. |
| 9/20/2025 | Core MVP and Development Start | Early version with scaffolding | Foundation for future features |
| 9/21/2025 | Finished Project Plan Template | Project planning | Finished planning for MVP project. |

## Project Status Tracking & Working Meeting Minutes

Attendance: Every team member has been involved with the discussions in our GROUPME and Microsoft teams

Progress & milestones: Login/ Logout functions were created, as well as the login screen was created.

Deliverables: 1

Next actions to create the functions and screens for the regular users and administration

# Project Work and Product Estimates

Inputs to estimation include:

- Deliverables listed in Section 4

- Major Milestones listed in Section 5

- Tasks and/or sub-tasks identified in the detailed project Schedule.

## Estimate Summary

Requirements – 40 hours

Development – 180 hours

Testing – 50 hours

Documentation – 30 hours

The tables below summarize the product size and effort estimates:

| OwlExchange | Estimate Attributes |  |  |
| --- | --- | --- | --- |
|  | Size |  |  |
| WBS areas | Unit of Size | Size | Effort |
| Total Requirements Effort (includes feature-related and "other" (non-feature) Requirements work) |  |  | 40 hours |
| Feature Related Requirements Size and Effort Totals | PAGES | 11 | 30 hours |
| Total Development Effort (includes feature-related and "other" (non-feature) Development work) |  |  | 200 hours |
| Feature Related Development Coding Size and Effort Totals | LOC | 3,000 | 180 hours |
| Feature Related Development Documentation Size and Effort | PAGES | 8 | 20 hours |
| Total Testing Effort (includes feature-related and "other" (non-feature) Testing work) |  |  | 50 hours |
| Feature Related Testing Size and Effort Totals | TEST CASES | 30 | 50 hours |
| Feature Level Effort Total (from Feature Estimate Worksheet) | LOC | 6,208 | 190 hours |
| Development Effort Total (Includes Feature Level and project level overhead for Requirements, Development, and Testing) |  |  | 220 hours |
| Project Level Effort Total (from Project Level Effort Estimates worksheet, excluding requirements, development, and testing) |  |  | 45 hours |
| Project Total Effort (Project Totals + Feature Totals) |  |  | 265 hours |

# Project Resource Requirements

## Staffing/ Skill Requirements

Role: Team Leader (Devin Perry)

Critical Skills

Communication, Problem Solving

Skill Gaps: Little experience with React, JavaScript and MS SQL

Role: Development Manager (Dawson White)

Critical Skills

Problem Solving, Version Control, Communication, Project Knowledge

Skill Gaps: Frontend development, Limited documentation experience

Role: Planning Manager (Scott Nguyen)

Critical Skills 
	Problem Solving, Organization

Skill Gaps: JavaScript, React, Backend, GitHub documentation

Role: Quality & Process Manager (Bee Tillman)

Critical Skills

Support Testing and Quality Checks

Skill Gaps: MS SQL, Frontend development

Role: Support Manager (Evan Tucker)

Critical Skills

General technical support, Adaptability, Teamwork

Skill Gaps: Database, Web building, JavaScript

## Plan to Fill Skill Gaps

Use online resources and rely on the group when trying to figure out the technologies required for the better use of the technologies required for the project.

# Dependencies and Constraints

## Constraints

Constraints of the current system include limited functionality to core MVP features, reliance on React, JavaScript and MS SQL technologies, and the absence of advanced features like item ratings and recommendations which are planned for future phases.

# Risk Management

## Risk Management Strategy

The team will continuously monitor progress throughout the development cycle. The potential risk whether it’s scheduling, technical or resource will be identified in the planning sessions. The team will emphasize modular design, review the code before the code is pushed to the main branch, and regular integration testing to detect issues early. Scheduling issues will be managed by maintaining clear milestones, using agile sprints, and having good time management into the project plan. Resource risks, like limited expertise or availability, knowledge sharing and documentation. Security and reliability risks are addressed through having good coding standards, secure authentication practices, and backup/recovery procedures. Finally, the team conducts ongoing reviews and status updates to manage risks, ensuring that emerging issues are promptly addressed and that the system remains aligned with project goals.

## Initial Risk List

This is the initial risk list. Descriptions are provided below the table. Risks with a pre-mitigation magnitude of 2.0 or below are not listed.

| Risk number | Risk Priority (H, M, L) | Likelihood of Occurrence | Risk name: brief description | Mitigation Strategy “ACCEPTED” or “MITIGATED” with pointer to plan. |
| --- | --- | --- | --- | --- |
| 1 | H | M | Database Connection Loss: Backend code could run into a bug that leads to data not being updated or retrieved correctly. | Mitigated: A plethora of tests will be run, and various pieces of data will be used to test the database. |
| 2 | M | H | Scope Creep: We could waste time and resources focusing on features that are not part of the MVP before MVP completion. | Mitigated: Meeting with sponsors will help keep MVP requirement concrete and the main focus throughout development. |
| 3 | M | M | Poor Documentation: Imprecise documentation may lead developers working on this project in the future to misinterpret the vision of the system which could lead to features not working together or confusing users. | Mitigated: All documentation will be reviewed by both the team and the sponsors. |
| 4 | M | L | Server Capacity Issues: Since this is initially a small-scale project, vast resources will most likely not be expended to gain access to relatively large server capacities. An unexpected surge of users could overwhelm the servers. | Mitigated: Time will be taken to research the expected amount of users interested in the system before release. |

# Project Configuration and Data Management

## Configuration Management

The OwlExchange project will use GitHub to manage all source code, SQL scripts, and project documents. Each team member will create separate branches for features or bug fixes, and changes will only be merged into the main brand after review to keep the code stable. Project documents including plans, and test documentation will also be stored in the repository under a dedicated folder for easy access.

Any major updates or changes will be logged as GitHub issues so the team can review and approve them before moving forward. GitHub will serve as the main backup, but the team lead will also keep local copies to prevent data loss. This process ensures that everything remains versioned, organized, and ready for future teams to build on.

# Project Process

## Software Life Cycle Model

The OwlExchange project will follow an iterative development approach based on the Agile methodology. Work will be broken into small milestones so that progress can be reviewed regularly and adjusted if needed. Each phase of the life cycle will include planning, design, implementation, testing, and review before moving on to the next set of tasks.

The team will rely on GitHub for version control and regular meetings to review progress and set goals. Testing will take alongside development to ensure new features work correctly before being merged into the main build. Documentation will be updated throughout the project so future teams can continue development smoothly.

This life cycle model supports flexibility, continuous feedback, and clear progress tracking, which is important as this project is designed as a multi-semester project.

# Referenced Documents

The following documents were used as references while creating this project plan:

OwlExchange Project Requirements Document – outlines the initial requirements and expectations for the MVP.

Project Schedule and Milestone Plan – used to set deadlines and track progress.

Design Document Template – provides the structure for creating the system design document that details the architecture and design choices.

IEEE 12207 Standard for Software Life Cycle Processes – used as a guideline for planning, development, and documentation.

# Glossary

MVP (Minimum Viable Product): A software product that includes features that have been agreed upon as the most basic and essential features of the system.

Agile: A way of developing software step by step, with regular feedback and improvements.

Repository: A storage place (like GitHub) where we keep all the code and documents for the project.

Branch: A separate copy of the code used to work on new features without affecting the main version.

SQL (Structured Query Language): A language used to interact with the database where user and item information is stored.

# Change Record

9/17/2025 Added Express.js as part as the tech stack as well as writing out the project schedules and deliverables, Dawson White modified the project plan.

9/18/2025: Added node.js to the software being used on the project, makes the runtime for npm to work and provides server support, Devin Perry modified the project plan.

9/20/2025: Added the milestone of the login/ logout functionality as well as the actual login screen. Added the milestone to the milestone section of the project plan. Devin Perry modified the project plan.

9/21/2025: Added all accomplished milestones up to the Project Planning due date in the milestones section of the project plan. Scott Nguyen modified the project plan.